## Acceptance Matrix
Test ID | Domain | Subdomain | Scenario | Preconditions | Steps | Expected Result | Actor | Test Level | Automation | Priority | Release Gate | Spec Ref | Baseline Impl. | Execution Status | Evidence / Notes | Owner Sprint
PUB-001 | Public Marketplace | Public access | Anonymous user can browse homepage | No session. | Open `/`. | Homepage renders without login and exposes public marketplace navigation. | Anonymous | E2E | Automated | P0 | Blocking | L12-L25 | DONE | Not Run
PUB-002 | Public Marketplace | Public access | Anonymous user can browse approved listings | Approved listings exist. | Open `/listados`. | Approved public inventory is visible without authentication. | Anonymous | E2E | Automated | P0 | Blocking | L12-L25 | DONE | Not Run
PUB-003 | Public Marketplace | Public access | Anonymous user can open an approved listing detail | Approved listing exists. | Open its detail URL. | Listing detail is readable without authentication. | Anonymous | E2E | Automated | P0 | Blocking | L12-L25 | DONE | Not Run
PUB-004 | Public Marketplace | Public access | Anonymous user can open an active public store page | Active store exists. | Open store URL. | Store page and eligible inventory are public. | Anonymous | E2E | Automated | P1 | Blocking | L12-L25 | DONE | Not Run
PUB-005 | Public Marketplace | Public access | Private account features do not block public browsing | No session. | Browse catalog, detail and store pages. | No forced signup/login occurs for normal browsing. | Anonymous | E2E | Automated | P0 | Blocking | L12-L25 | DONE | Not Run
PUB-006 | Public Marketplace | Public access | Marketplace copy does not claim Laria processes payment | Public pages available. | Inspect purchase/contact trust copy. | Copy does not imply checkout, escrow, delivery management or transaction guarantee. | Anonymous | Manual | Manual | P0 | Blocking | L12-L25 | DONE | Not Run
PUB-007 | Public Marketplace | Public access | No internal chat entry point is exposed as a working V1 feature | Public and account pages available. | Inspect primary marketplace actions. | Contact path remains external/WhatsApp; no fake internal-chat workflow is offered. | All | Manual | Manual | P1 | Blocking | L12-L25 | DONE | Not Run
AUTH-001 | Accounts & Authentication | Particular account | Particular signup succeeds with required profile data | Unique email and phone. | Complete signup with valid name/email/password/WhatsApp/location. | Auth user and Particular profile are created; confirmation behavior follows configuration. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Pass | Owner manual production retest PASS — 2026-09-10
AUTH-002 | Accounts & Authentication | Particular account | Duplicate email signup is rejected cleanly | Existing auth email. | Attempt signup with same email. | User gets safe duplicate-account guidance; no duplicate account/profile is created. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-003 | Accounts & Authentication | Particular account | Email confirmation completes signup | Unconfirmed Particular signup. | Follow valid confirmation link. | Session/profile complete and user reaches intended success/account destination. | Particular | E2E | Both | P0 | Blocking | L27-L57 | MODIFY | Pass | Owner manual production retest PASS — 2026-09-10
AUTH-004 | Accounts & Authentication | Particular account | Expired/invalid confirmation link fails safely | Invalid or expired link. | Open callback link. | No session corruption; user sees a recoverable error path. | Particular | E2E | Automated | P1 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-005 | Accounts & Authentication | Particular account | Password login succeeds | Confirmed account. | Login with correct email/password. | Authenticated session established and account area accessible. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-006 | Accounts & Authentication | Particular account | Password login rejects wrong password | Confirmed account. | Login with wrong password. | Authentication fails without revealing sensitive account details. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-007 | Accounts & Authentication | Particular account | Magic-link login succeeds for existing user | Existing account. | Request and follow magic link. | Session established; no new user is created. | Particular | E2E | Both | P1 | Blocking | L27-L57 | MODIFY | Pass | Owner manual production retest PASS — 2026-09-10
AUTH-008 | Accounts & Authentication | Particular account | Magic-link login does not create unknown user | Unregistered email. | Request login magic link. | No unintended account is created. | Anonymous | API | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-009 | Accounts & Authentication | Particular account | Logout clears protected session | Authenticated account. | Log out then open `/mi-cuenta`. | User is signed out and protected page redirects to login. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-010 | Accounts & Authentication | Particular account | Forgot-password request succeeds for valid account | Existing account. | Submit forgot-password flow. | Recovery message is sent/queued without exposing credentials. | Particular | E2E | Both | P0 | Blocking | L27-L57 | MODIFY | Pass | Owner manual production retest PASS — 2026-09-10
AUTH-011 | Accounts & Authentication | Particular account | Forgot-password request is safe for unknown email | Unknown email. | Submit forgot-password request. | Response does not leak unsafe directory data and no account is created. | Anonymous | API | Automated | P1 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-012 | Accounts & Authentication | Particular account | Valid password-reset link changes password | Recovery link available. | Open recovery link, set new password, sign in. | New password works; old password no longer works. | Particular | E2E | Both | P0 | Blocking | L27-L57 | MODIFY | Pass | Owner manual production retest PASS — 2026-09-10
AUTH-013 | Accounts & Authentication | Particular account | Expired password-reset link fails safely | Expired recovery link. | Attempt reset. | Password unchanged and recoverable error shown. | Particular | E2E | Automated | P1 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-014 | Accounts & Authentication | Particular account | Authenticated user can change password | Logged-in account. | Use account password-change flow. | Password changes and future login uses new password. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-015 | Accounts & Authentication | Particular account | Profile editing updates allowed fields | Logged-in Particular. | Change name, WhatsApp, city and region. | Profile persists new values. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-016 | Accounts & Authentication | Particular account | Particular account supports buyer and seller features | Logged-in Particular. | Access favorites/search-alert area and seller publication area. | Same account can buy-side and sell-side without second account. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-017 | Accounts & Authentication | Particular account | Store-owner route does not silently convert a Particular account | Logged-in Particular. | Attempt store-owner-only setup route. | Account type is not silently changed; safe recovery/denial shown. | Particular | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Pass | Automated local account-separation regression PASS — 2026-09-10
AUTH-018 | Accounts & Authentication | Particular account | Store-owner account remains separate from Particular | Store-owner account exists. | Inspect account role and Particular seller routes. | Store-owner identity is not treated as a Particular account. | Store Owner | E2E | Automated | P0 | Blocking | L27-L57 | MODIFY | Pass | Automated local account-separation regression PASS — 2026-09-10
AUTH-019 | Accounts & Authentication | Particular account | Protected account route redirects unauthenticated user preserving return path | No session. | Open protected account route. | Redirects to login and preserves safe return destination. | Anonymous | E2E | Automated | P1 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-020 | Accounts & Authentication | Particular account | Unsafe external `next` redirect is rejected | Crafted external next URL. | Invoke auth callback/login return flow. | Redirect remains same-site. | Anonymous | API | Automated | P0 | Blocking | L27-L57 | MODIFY | Not Run
AUTH-021 | Accounts & Authentication | Particular account | Account email-change workflow is absent from V1 UI | Authenticated account. | Inspect account settings. | No unsupported email-change workflow is presented as active. | Particular | Manual | Manual | P2 | Non-blocking | L27-L57 | MODIFY | Not Run
AUTH-022 | Accounts & Authentication | Particular account | Account deletion workflow is absent from V1 UI | Authenticated account. | Inspect account settings. | No unsupported self-delete workflow is presented as active. | Particular | Manual | Manual | P2 | Non-blocking | L27-L57 | MODIFY | Not Run
LIST-001 | Listings | Creation & ownership | Unauthenticated user cannot publish | No session. | Open `/vender`. | User is redirected to login; return path is preserved. | Anonymous | E2E | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-002 | Listings | Creation & ownership | Authenticated Particular can open publication form | Logged-in Particular. | Open `/vender`. | Publication form is available. | Particular | E2E | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-003 | Listings | Creation & ownership | Valid Particular submission creates owned pending listing | Logged-in Particular, valid data/photos. | Submit listing. | Listing is created with owner_user_id=current user, seller_type individual, store_id null, status pending. | Particular | API/DB | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-004 | Listings | Creation & ownership | Particular cannot directly create approved listing | Logged-in Particular. | Tamper request/status during creation. | Protected status cannot be set to approved by seller. | Particular | DB/RLS | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-005 | Listings | Creation & ownership | Required title validation | Logged-in Particular. | Submit without title. | Submission blocked with clear validation; no partial listing finalized. | Particular | E2E | Automated | P1 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-006 | Listings | Creation & ownership | Required category validation | Logged-in Particular. | Submit without category. | Submission blocked; no invalid record finalized. | Particular | E2E | Automated | P1 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-007 | Listings | Creation & ownership | Instrument type required where category has meaningful subtypes | Category with configured instrument types. | Omit instrument type and submit. | Submission is rejected with user-facing validation. | Particular | E2E | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-008 | Listings | Creation & ownership | Instrument type not spuriously required where category has no subtype rule | Category without meaningful subtype. | Submit valid listing without instrument type. | Submission succeeds if all applicable requirements pass. | Particular | E2E | Automated | P1 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-009 | Listings | Creation & ownership | Dynamic attributes save correctly | Category with configured attributes. | Set several supported attributes and submit. | Attributes persist and render through user-facing labels. | Particular | E2E | Automated | P1 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-010 | Listings | Creation & ownership | Optional dynamic attributes may be omitted | Valid listing with no optional attributes. | Submit. | Listing can be submitted if no explicit required attribute is violated. | Particular | E2E | Automated | P1 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-011 | Listings | Creation & ownership | Raw JSON keys are not exposed in form/detail | Listing with attributes. | View form and detail. | Human-readable labels/options are shown instead of raw JSON/snake_case. | Particular | Manual | Both | P1 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-012 | Listings | Creation & ownership | Marketplace rules acceptance is required | Logged-in Particular. | Submit without accepting rules. | Submission rejected; acceptance timestamp not fabricated. | Particular | E2E | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-013 | Listings | Creation & ownership | Price accepts valid positive value | Logged-in Particular. | Submit valid positive price. | Price persists accurately in PEN. | Particular | E2E | Automated | P1 | Blocking | L59-L79,L99-L115 | MODIFY | Fail | Owner production acceptance FAIL — S/ 1,200 rendered as S/ 1,197 — 2026-09-15; fix awaits owner retest.
LIST-014 | Listings | Creation & ownership | Invalid negative price is rejected | Logged-in Particular. | Submit negative price. | Validation/database constraint rejects it. | Particular | API/DB | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-015 | Listings | Creation & ownership | Profile identity is used for owned listing display | Owned approved listing; profile exists. | Open listing detail. | Seller identity/contact resolves from current profile where specified. | Particular | E2E | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-016 | Listings | Creation & ownership | Profile name update propagates to owned listing display | Owned listing exists. | Change profile name; reload detail. | Listing seller display reflects current profile name. | Particular | E2E | Automated | P1 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-017 | Listings | Creation & ownership | Profile WhatsApp update propagates to owned listing contact | Owned listing exists. | Change profile phone; invoke contact. | Current profile WhatsApp is used. | Particular | E2E | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-018 | Listings | Creation & ownership | Legacy listing without owner keeps historical contact fallback | Legacy owner_user_id null listing exists. | Open detail/contact. | Historical listing-level contact data continues to work. | Anonymous | E2E | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-019 | Listings | Creation & ownership | New account does not auto-claim legacy listing by matching phone | Legacy listing matches user's phone. | Create/login account. | owner_user_id remains unchanged until admin manually links it. | Particular | DB/RLS | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-020 | Listings | Creation & ownership | Submission cannot assign another user's owner_user_id | Two Particular accounts. | Tamper submission owner ID. | RLS/server validation prevents cross-account ownership. | Particular | DB/RLS | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-021 | Listings | Creation & ownership | Submission retry does not duplicate listing | Valid submission; simulate lost response. | Retry same submission capability. | Exactly one listing finalizes. | Particular | API/DB | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
LIST-022 | Listings | Creation & ownership | Changed payload cannot misuse old retry token | Issued retry token for one payload. | Retry using materially changed values/files. | Server rejects unsafe reuse or requires fresh capability; no overwrite/duplication. | Particular | API | Automated | P0 | Blocking | L59-L79,L99-L115 | MODIFY | Not Run
PHOTO-001 | Listings | Photos | Exactly 2 valid photos is accepted | Logged-in Particular. | Submit with exactly two valid images. | Submission passes photo-count validation. | Particular | E2E | Automated | P0 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-002 | Listings | Photos | 1 photo is rejected | Logged-in Particular. | Submit with one image. | Submission blocked; minimum 2 stated. | Particular | E2E | Automated | P0 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-003 | Listings | Photos | Exactly 10 photos is accepted | Logged-in Particular. | Submit with ten valid images. | Submission succeeds if all other requirements pass. | Particular | E2E | Automated | P0 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-004 | Listings | Photos | 11 photos is rejected | Logged-in Particular. | Attempt eleven images. | Client/server enforce maximum 10. | Particular | E2E | Automated | P0 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-005 | Listings | Photos | Supported JPEG upload works | Valid JPEG under size limit. | Upload and submit. | Image stored and associated. | Particular | E2E | Automated | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-006 | Listings | Photos | Supported PNG upload works | Valid PNG under size limit. | Upload and submit. | Image stored and associated. | Particular | E2E | Automated | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-007 | Listings | Photos | Supported WebP upload works | Valid WebP under size limit. | Upload and submit. | Image stored and associated. | Particular | E2E | Automated | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-008 | Listings | Photos | Unsupported file type is rejected | Non-image/unsupported format. | Upload. | Rejected before finalization with useful message. | Particular | E2E | Automated | P0 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-009 | Listings | Photos | Oversized file is rejected | Image over storage limit. | Upload. | Rejected; no invalid photo row finalized. | Particular | E2E | Automated | P0 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-010 | Listings | Photos | Photo reorder changes primary image | Owned editable listing with >=3 photos. | Reorder images and save. | sort_order persists and first image becomes catalog primary. | Particular | E2E | Automated | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-011 | Listings | Photos | Photo replacement preserves valid listing | Owned listing with >=2 photos. | Replace one image. | New image becomes associated; old image is no longer used; listing remains valid. | Particular | E2E | Automated | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-012 | Listings | Photos | Photo removal allowed while >=2 remain | Owned listing with 3+ photos. | Remove one and save. | Removal succeeds while count remains >=2. | Particular | E2E | Automated | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-013 | Listings | Photos | Photo removal blocked below minimum | Owned listing with 2 photos. | Attempt to remove one. | Operation blocked or revision cannot publish below 2. | Particular | E2E | Automated | P0 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-014 | Listings | Photos | Partial upload failure is recoverable | Valid submission; force later upload failure. | Retry without closing page. | Previously hardened retry/cleanup flow recovers without duplicate listing. | Particular | Integration | Automated | P0 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-015 | Listings | Photos | Closing page mid-upload may leave orphan but must not create public listing | Interrupt browser during upload. | Close before finalization then inspect DB/public catalog. | No finalized/public invalid listing exists; known orphan-storage limitation only. | Particular | Integration | Both | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-016 | Listings | Photos | Card uses optimized responsive image rather than eager original | Approved listing. | Inspect rendered card/network behavior. | Responsive optimized image path/sizes are used. | Anonymous | Performance | Both | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
PHOTO-017 | Listings | Photos | Detail thumbnails are lazy/responsive | Approved listing with many photos. | Open detail and inspect network. | Thumbnails do not eagerly download all full-size originals. | Anonymous | Performance | Both | P1 | Blocking | L79-L79,L286-L302 | MODIFY | Not Run
RLS-001 | Security & Ownership | Listing RLS | Owner can read own pending listing | Particular owns pending listing. | Query/open account listing. | Owner can access it in account context. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-002 | Security & Ownership | Listing RLS | Owner can read own rejected listing | Particular owns rejected listing. | Open account listing. | Owner can see status/reason as allowed. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-003 | Security & Ownership | Listing RLS | Unrelated Particular cannot read another user's nonpublic listing | Two users; pending listing owned by A. | B attempts direct data access. | Access denied/no row returned. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-004 | Security & Ownership | Listing RLS | Unrelated Particular cannot update another user's listing | Two users. | B attempts update to A listing. | Update denied. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-005 | Security & Ownership | Listing RLS | Owner cannot mutate protected status directly | Owned listing. | Attempt direct status update. | Trigger/RLS blocks protected-field change. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-006 | Security & Ownership | Listing RLS | Owner cannot mutate published_at directly | Owned listing. | Attempt published_at update. | Change blocked. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-007 | Security & Ownership | Listing RLS | Owner cannot mutate view_count directly | Owned listing. | Attempt view_count update. | Change blocked. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-008 | Security & Ownership | Listing RLS | Owner cannot change seller_type to store | Owned individual listing. | Tamper seller_type. | Change blocked. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-009 | Security & Ownership | Listing RLS | Owner cannot attach arbitrary store_id | Owned individual listing. | Tamper store_id. | Change blocked. | Particular | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-010 | Security & Ownership | Listing RLS | Admin retains moderation authority | Admin + pending listing. | Approve/reject via trusted path. | Authorized admin action succeeds. | Admin | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-011 | Security & Ownership | Listing RLS | Public reads only publicly eligible inventory | Mix approved/pending/rejected/hidden/sold. | Query public catalog. | Only approved active inventory appears. | Anonymous | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
RLS-012 | Security & Ownership | Listing RLS | Public photo access follows eligible listing state | Photos across listing states. | Attempt public photo relation reads. | Public app/data exposure follows listing visibility rules. | Anonymous | DB/RLS | Automated | P0 | Blocking | L87-L97,L115-L115,L246-L252 | MODIFY | Pass | Automated local SQL/RLS regression PASS — 2026-09-10
LIFE-001 | Listings | Lifecycle | Admin approval publishes pending Particular listing | Pending valid listing. | Admin approves. | Status becomes approved and public; first publication timestamp set. | Admin | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Not Run
LIFE-002 | Listings | Lifecycle | Admin rejection keeps listing nonpublic | Pending listing. | Admin rejects with reason. | Listing not public; owner sees rejection reason; email workflow eligible. | Admin | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Not Run
LIFE-003 | Listings | Lifecycle | Owner hides approved listing | Approved owned listing. | Choose hide/unpublish. | Listing disappears from public browse. | Particular | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
LIFE-004 | Listings | Lifecycle | Owner restores hidden valid Particular listing through normal rules | Hidden owned listing. | Restore. | Listing returns through required publication/moderation behavior. | Particular | E2E | Automated | P1 | Blocking | L81-L97 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
LIFE-005 | Listings | Lifecycle | Owner marks approved listing sold | Approved owned listing. | Mark sold. | Listing status becomes sold; removed from normal catalog. | Particular | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
LIFE-006 | Listings | Lifecycle | Sold listing remains reachable by direct URL | Sold listing with known slug. | Open direct URL. | Page renders with clear Vendido state. | Anonymous | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
LIFE-007 | Listings | Lifecycle | Sold listing is absent from normal search/catalog | Sold listing exists. | Search/browse matching catalog. | Sold item is not returned as active inventory. | Anonymous | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Not Run
LIFE-008 | Listings | Lifecycle | Sold listing cannot be directly reactivated | Sold owned listing. | Attempt restore/status manipulation. | Original historical record stays sold. | Particular | DB/RLS | Automated | P0 | Blocking | L81-L97 | MODIFY | Not Run
LIFE-009 | Listings | Lifecycle | Relist copies sold listing | Sold owned listing. | Choose Relistar. | New listing/draft-copy created; original sold row unchanged. | Particular | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
LIFE-010 | Listings | Lifecycle | Relisted Particular copy requires moderation | Relisted copy valid. | Submit relisted copy. | New record enters pending, not approved. | Particular | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Not Run
LIFE-011 | Listings | Lifecycle | Relisted normal Tienda copy requires moderation | Normal Tienda sold listing. | Relist. | Copy enters pending. | Store Owner | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Not Run
LIFE-012 | Listings | Lifecycle | Relisted Tienda Verificada copy can publish directly | Verified store sold listing. | Relist valid copy. | New copy can publish approved directly. | Store Owner | E2E | Automated | P0 | Blocking | L81-L97 | MODIFY | Not Run
LIFE-013 | Listings | Lifecycle | Historical sold record preserves transaction/review linkage | Sold listing with verified transaction/reviews. | Relist copy. | Old listing retains historical relations; copy has new identity. | Admin | DB | Automated | P0 | Blocking | L81-L97 | MODIFY | Blocked | Deferred — requires the later verified-transaction/review system.
LIFE-014 | Listings | Lifecycle | No normal hard-delete control exists for seller | Owned listing. | Inspect listing actions. | Hide/sold/relist exist as appropriate; no destructive hard delete. | Particular | Manual | Manual | P1 | Blocking | L81-L97 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
REV-001 | Listings | Approved listing revisions | Immediate price edit applies without moderation | Approved Particular listing. | Change price only. | Public approved listing reflects new price immediately. | Particular | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Not Run
REV-002 | Listings | Approved listing revisions | Immediate description edit applies without moderation | Approved Particular listing. | Change description only. | Public listing updates without pending revision. | Particular | E2E | Automated | P1 | Blocking | L117-L137 | BUILD | Not Run
REV-003 | Listings | Approved listing revisions | Immediate location edit applies without moderation | Approved Particular listing. | Change location only. | Public listing updates directly. | Particular | E2E | Automated | P1 | Blocking | L117-L137 | BUILD | Not Run
REV-004 | Listings | Approved listing revisions | Immediate attribute edit applies without moderation | Approved Particular listing. | Change detailed attributes only. | Public listing updates directly. | Particular | E2E | Automated | P1 | Blocking | L117-L137 | BUILD | Not Run
REV-005 | Listings | Approved listing revisions | Title edit creates pending revision for Particular | Approved listing. | Change title. | Live version remains unchanged; pending revision stores new title. | Particular | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
REV-006 | Listings | Approved listing revisions | Category edit creates pending revision | Approved listing. | Change category. | Old approved version remains live while revision awaits review. | Particular | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Not Run
REV-007 | Listings | Approved listing revisions | Instrument type edit creates pending revision | Approved listing. | Change instrument type. | Old approved version remains live. | Particular | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Not Run
REV-008 | Listings | Approved listing revisions | Brand edit creates pending revision | Approved listing. | Change brand. | Pending revision created; live row not prematurely mutated. | Particular | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Not Run
REV-009 | Listings | Approved listing revisions | Model edit creates pending revision | Approved listing. | Change model. | Pending revision created. | Particular | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Not Run
REV-010 | Listings | Approved listing revisions | Photo edit creates pending revision | Approved listing. | Replace/reorder moderated photo set. | Public approved photo version stays live pending review. | Particular | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
REV-011 | Listings | Approved listing revisions | Mixed immediate + moderated edit is handled consistently | Approved listing. | Change price and title in one save. | Moderated fields do not leak live before approval; defined immediate-field behavior remains consistent/atomic. | Particular | Integration | Automated | P0 | Blocking | L117-L137 | BUILD | Fail | Owner production acceptance FAIL — mixed moderated/photo edit returned an action error — 2026-09-15; fix awaits owner retest.
REV-012 | Listings | Approved listing revisions | Admin approves pending revision | Pending revision exists. | Admin reviews and approves. | Approved public version atomically adopts revision; revision history retained. | Admin | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Fail | Owner production acceptance FAIL — approved title was not the primary public title — 2026-09-15; fix awaits owner retest.
REV-013 | Listings | Approved listing revisions | Admin rejects pending revision | Pending revision exists. | Reject with reason. | Old approved version remains public; owner sees reason; revision marked rejected. | Admin | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
REV-014 | Listings | Approved listing revisions | Additional moderated edits safely amend the existing pending proposal | Approved listing with one pending moderated revision. | Change another moderated field or the proposed photos before the admin decision. | Exactly one pending revision remains and contains the latest complete proposed moderated state. | Particular | Integration | Automated | P0 | Blocking | L117-L137 | BUILD | Fail | Requirement updated for amendable pending proposals; implementation awaits owner production retest — 2026-09-16.
REV-015 | Listings | Approved listing revisions | Normal Tienda uses same moderated revision rules | Approved normal-store listing. | Change moderated field. | Old version remains public pending admin review. | Store Owner | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
REV-016 | Listings | Approved listing revisions | Tienda Verificada bypasses moderated revision | Verified-store listing. | Edit title/photos. | Qualifying edit applies directly; no listing-by-listing revision approval required. | Store Owner | E2E | Automated | P0 | Blocking | L117-L137 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
DASH-001 | Particular Dashboard | Management | Account shows all owned listing states | Particular owns approved/pending/rejected/hidden/sold listings. | Open `/mi-cuenta`. | All owned listings are represented with correct status. | Particular | E2E | Automated | P0 | Blocking | L99-L115 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
DASH-002 | Particular Dashboard | Management | Dashboard opens listing management action | Owned listing exists. | Open from account table. | Correct listing/manage route opens. | Particular | E2E | Automated | P1 | Blocking | L99-L115 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
DASH-003 | Particular Dashboard | Management | Dashboard shows rejection reason | Rejected listing with reason. | Open account. | Reason is visible to owner. | Particular | E2E | Automated | P0 | Blocking | L99-L115 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
DASH-004 | Particular Dashboard | Management | Dashboard offers hide action where valid | Approved listing. | Inspect actions. | Hide/unpublish is available. | Particular | E2E | Automated | P1 | Blocking | L99-L115 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
DASH-005 | Particular Dashboard | Management | Dashboard offers sold action where valid | Approved listing. | Inspect actions. | Mark sold is available. | Particular | E2E | Automated | P1 | Blocking | L99-L115 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
DASH-006 | Particular Dashboard | Management | Dashboard offers relist for sold listing | Sold listing. | Inspect actions. | Relistar is available; direct restore is not. | Particular | E2E | Automated | P1 | Blocking | L99-L115 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
DASH-007 | Particular Dashboard | Management | Dashboard has no fake metric values | Logged-in Particular. | Inspect analytics cards before/with data. | Metrics are real or clearly empty; no placeholder analytics presented as factual. | Particular | Manual | Both | P0 | Blocking | L99-L115 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
SANA-001 | Analytics | Seller analytics | Per-listing view count is displayed | Owned listing has views. | Open seller analytics. | Displayed view count matches analytics source. | Particular | Integration | Automated | P1 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-002 | Analytics | Seller analytics | Per-listing favorite count is displayed | Owned listing has favorites. | Open analytics. | Count matches stored favorite data. | Particular | Integration | Automated | P1 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-003 | Analytics | Seller analytics | Per-listing WhatsApp contact count is displayed | Owned listing has contact events. | Open analytics. | Count matches qualifying events. | Particular | Integration | Automated | P0 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-004 | Analytics | Seller analytics | Per-listing publication date/status/sold state display correctly | Mixed listings. | Open analytics. | Metadata matches listing lifecycle. | Particular | E2E | Automated | P1 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-005 | Analytics | Seller analytics | Account active-listing aggregate is correct | Owned mixed states. | Compare dashboard total with DB. | Only active definition used by product is counted consistently. | Particular | Integration | Automated | P1 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-006 | Analytics | Seller analytics | Account total views aggregate is correct | Multiple owned listings with views. | Compare. | Aggregate equals underlying records/events. | Particular | Integration | Automated | P1 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-007 | Analytics | Seller analytics | Account favorites aggregate is correct | Favorites across listings. | Compare. | Aggregate is correct. | Particular | Integration | Automated | P1 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-008 | Analytics | Seller analytics | Account WhatsApp contacts aggregate is correct | Contact events across listings. | Compare. | Aggregate is correct without message-content data. | Particular | Integration | Automated | P0 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-009 | Analytics | Seller analytics | Sold listings aggregate is correct | Several sold listings. | Compare. | Sold count equals lifecycle records. | Particular | Integration | Automated | P1 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
SANA-010 | Analytics | Seller analytics | Revenue is not fabricated | Transactions occur off-platform. | Inspect dashboards. | No invented revenue/GMV is displayed. | Particular | Manual | Manual | P0 | Blocking | L111-L115,L205-L215 | BUILD | Not Run
STORE-001 | Stores | Owner account & application | Store owner account can be created separately | Unique email. | Complete store-owner account setup. | Profile uses store-owner role and is not a Particular account. | Store Owner | E2E | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-002 | Stores | Owner account & application | One V1 store is bound to its owner account | Store-owner account. | Complete application. | Store owner_user_id/membership links correctly. | Store Owner | DB/RLS | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-003 | Stores | Owner account & application | Store application requires RUC | Store owner logged in. | Submit without RUC. | Submission blocked. | Store Owner | E2E | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-004 | Stores | Owner account & application | Store application requires business identity/razon social | Store owner logged in. | Omit required business identity. | Submission blocked. | Store Owner | E2E | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-005 | Stores | Owner account & application | Store application requires email | Store owner logged in. | Omit email. | Submission blocked. | Store Owner | E2E | Automated | P1 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-006 | Stores | Owner account & application | Store application requires phone | Store owner logged in. | Omit phone. | Submission blocked. | Store Owner | E2E | Automated | P1 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-007 | Stores | Owner account & application | Store application requires physical address | Store owner logged in. | Omit address. | Submission blocked. | Store Owner | E2E | Automated | P1 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-008 | Stores | Owner account & application | Store application requires geographic location | Store owner logged in. | Omit required location. | Submission blocked. | Store Owner | E2E | Automated | P1 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-009 | Stores | Owner account & application | Store application requires contact person | Store owner logged in. | Omit contact person. | Submission blocked. | Store Owner | E2E | Automated | P1 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-010 | Stores | Owner account & application | Optional store photos can be submitted | Valid application. | Attach valid optional store photos. | Application accepts and stores them. | Store Owner | E2E | Automated | P2 | Non-blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-011 | Stores | Owner account & application | Optional logo/banner/socials can be omitted | Valid required data only. | Submit. | Application succeeds without optional assets/socials. | Store Owner | E2E | Automated | P1 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-012 | Stores | Owner account & application | Optional logo/banner/socials save when provided | Valid application with optional fields. | Submit. | Values/assets persist and render when public. | Store Owner | E2E | Automated | P1 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-013 | Stores | Owner account & application | Duplicate RUC is rejected | Existing store with same RUC. | Submit another application. | Duplicate store is not silently created. | Store Owner | DB | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-014 | Stores | Owner account & application | RUC uniqueness is concurrency-safe | Two simultaneous applications with same new RUC. | Submit concurrently. | At most one succeeds; database constraint/invariant holds. | Store Owner | DB/Concurrency | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-015 | Stores | Owner account & application | Store page is not public before basic admin approval | Pending store. | Open public slug. | Public page is not exposed. | Anonymous | E2E | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-016 | Stores | Owner account & application | Pending store owner may submit listings | Store application pending. | Create inventory listing. | Submission is accepted into normal moderation if within cap. | Store Owner | E2E | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
STORE-017 | Stores | Owner account & application | Store owner cannot manage another store | Two stores/owners. | Owner A attempts B store update. | Denied. | Store Owner | DB/RLS | Automated | P0 | Blocking | L139-L154 | MODIFY | Pass | Automated local SQL/API integration PASS — 2026-09-10
VERIFY-001 | Stores | Approval & verification | Basic admin approval makes store public as Tienda | Pending valid store. | Admin approves. | Store page becomes public with Tienda label. | Admin | E2E | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-002 | Stores | Approval & verification | Normal Tienda listings still require moderation | Active nonverified store. | Submit valid listing. | Listing enters pending rather than direct approved. | Store Owner | E2E | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-003 | Stores | Approval & verification | Admin can mark eligible store Tienda Verificada | Active store with verification data. | Admin verifies. | is_verified/public trust state changes; direct-publication privilege enabled. | Admin | E2E | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-004 | Stores | Approval & verification | Verified store can publish qualifying new listing directly | Verified store within cap. | Submit valid listing. | Listing becomes approved/public without per-listing admin moderation. | Store Owner | E2E | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-005 | Stores | Approval & verification | Verification auto-approves current pending store listings | Store has several pending listings. | Admin verifies store. | All qualifying/current pending listings for that store become approved. | Admin | DB/Integration | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-006 | Stores | Approval & verification | Verification does not resurrect rejected listings | Store has rejected listing. | Verify store. | Rejected remains rejected. | Admin | DB | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-007 | Stores | Approval & verification | Verification does not resurrect hidden listings | Store has hidden listing. | Verify store. | Hidden remains hidden. | Admin | DB | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-008 | Stores | Approval & verification | Verification does not alter sold listings | Store has sold listing. | Verify store. | Sold remains sold/history intact. | Admin | DB | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-009 | Stores | Approval & verification | Verification transition is atomic with pending inventory approval | Store with pending inventory. | Force concurrent/partial failure around verification. | No half-verified inconsistent state; invariant holds. | Admin | DB/Concurrency | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-010 | Stores | Approval & verification | Revoking verification removes direct-publication privilege | Verified store. | Admin revokes; submit next listing. | Existing approved inventory stays approved; new listing requires moderation. | Admin | E2E | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-011 | Stores | Approval & verification | Revoking verification does not hide approved listings | Verified store with public inventory. | Revoke. | Previously approved listings remain public. | Admin | E2E | Automated | P0 | Blocking | L156-L165 | MODIFY | Pass | Automated local SQL/integration PASS — 2026-09-10
VERIFY-012 | Stores | Approval & verification | Exactly two public trust labels are used | Normal and verified stores exist. | Inspect public cards/pages. | Only Tienda and Tienda Verificada semantics are presented. | Anonymous | Manual | Manual | P1 | Blocking | L156-L165 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-13
VERIFY-013 | Stores | Approval & verification | Verification UI does not imply payment guarantee | Verified store. | Inspect badge/help copy. | Verification is framed as business identity/direct-publication trust, not transaction guarantee. | Anonymous | Manual | Manual | P0 | Blocking | L156-L165 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-13
CAP-001 | Stores | 50 concurrent listing cap | Store can have 50 concurrent pending/approved listings | Store has 49 concurrent. | Submit one valid listing. | 50th concurrent listing succeeds. | Store Owner | Integration | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-002 | Stores | 50 concurrent listing cap | 51st concurrent listing is rejected gracefully | Store has 50 concurrent. | Submit another. | Rejected with clear cap message; no partial finalization. | Store Owner | Integration | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-003 | Stores | 50 concurrent listing cap | Pending listings count toward cap | Store near cap. | Add pending listing then another. | Pending contributes to concurrent count. | Store Owner | DB | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-004 | Stores | 50 concurrent listing cap | Approved listings count toward cap | Store near cap. | Approve inventory then submit. | Approved contributes to cap. | Store Owner | DB | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-005 | Stores | 50 concurrent listing cap | Sold listings do not count | Store at cap; mark one sold. | Submit replacement. | New slot is available. | Store Owner | Integration | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-006 | Stores | 50 concurrent listing cap | Rejected listings do not count | Store has rejected inventory. | Calculate/submit. | Rejected rows do not consume concurrent capacity. | Store Owner | DB | Automated | P1 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-007 | Stores | 50 concurrent listing cap | Archived listings do not count | Store has archived inventory. | Calculate/submit. | Archived rows do not consume cap. | Store Owner | DB | Automated | P1 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-008 | Stores | 50 concurrent listing cap | Hidden listings do not count while hidden | Store at cap; hide one. | Submit new. | Hidden row frees a concurrent slot. | Store Owner | Integration | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-009 | Stores | 50 concurrent listing cap | Restoring hidden listing fails at full cap | Store has 50 concurrent plus hidden listing. | Attempt restore hidden. | Restore fails gracefully without exceeding 50. | Store Owner | Integration | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-010 | Stores | 50 concurrent listing cap | Concurrent submissions cannot exceed 50 | Store at 49; two simultaneous submissions. | Submit concurrently. | Atomic enforcement permits at most one additional concurrent listing. | Store Owner | DB/Concurrency | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
CAP-011 | Stores | 50 concurrent listing cap | Verification auto-approval cannot bypass cap invariant | Pending/approved mix near cap. | Verify store. | Result never creates >50 concurrent eligible rows unexpectedly. | Admin | DB/Concurrency | Automated | P0 | Blocking | L167-L171 | BUILD | Pass | Automated local SQL/concurrency integration PASS — 2026-09-10
SDASH-001 | Store Dashboard | Management & analytics | Store owner sees own store profile and inventory | Owned store exists. | Open dashboard. | Correct store and all manageable inventory states shown. | Store Owner | E2E | Automated | P0 | Blocking | L173-L177 | BUILD | Pass | Owner manual production retest PASS — 2026-09-13
SDASH-002 | Store Dashboard | Management & analytics | Store owner can edit allowed business/contact fields | Owned store. | Edit allowed profile fields. | Changes persist; protected admin fields cannot be changed. | Store Owner | E2E | Automated | P0 | Blocking | L173-L177 | BUILD | Not Run
SDASH-003 | Store Dashboard | Management & analytics | Store owner can manage logo/banner/photos/social links | Owned store. | Add/change/remove supported optional assets/links. | Changes persist within allowed rules. | Store Owner | E2E | Automated | P1 | Blocking | L173-L177 | BUILD | Not Run
SDASH-004 | Store Dashboard | Management & analytics | Store owner sees moderation reasons | Rejected/pending items with reasons. | Open dashboard. | Reasons/statuses visible. | Store Owner | E2E | Automated | P0 | Blocking | L173-L177 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
SDASH-005 | Store Dashboard | Management & analytics | Store owner can mark listing sold | Owned approved store listing. | Mark sold. | Lifecycle updates correctly. | Store Owner | E2E | Automated | P0 | Blocking | L173-L177 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
SDASH-006 | Store Dashboard | Management & analytics | Store owner can hide/unpublish listing | Owned approved listing. | Hide. | Public inventory updates correctly. | Store Owner | E2E | Automated | P1 | Blocking | L173-L177 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
SDASH-007 | Store Dashboard | Management & analytics | Store owner can relist sold item | Sold store listing. | Relist. | Copy behavior respects Tienda/Verificada moderation rules. | Store Owner | E2E | Automated | P0 | Blocking | L173-L177 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
SDASH-008 | Store Dashboard | Management & analytics | Store analytics totals match listing event data | Store with events. | Open aggregate analytics. | Impressions/views/favorites/contacts/sold totals reconcile. | Store Owner | Integration | Automated | P0 | Blocking | L173-L177 | BUILD | Not Run
SDASH-009 | Store Dashboard | Management & analytics | Store conversion ratios use meaningful denominators | Store with known event counts. | Inspect conversion metrics. | Ratios are mathematically consistent and avoid divide-by-zero errors. | Store Owner | Unit/Integration | Automated | P1 | Blocking | L173-L177 | BUILD | Not Run
SDASH-010 | Store Dashboard | Management & analytics | Store dashboard never invents revenue | Off-platform sales only. | Inspect dashboard. | No revenue/GMV figures are fabricated. | Store Owner | Manual | Manual | P0 | Blocking | L173-L177 | BUILD | Pass | Owner manual production acceptance PASS — 2026-09-15
FAV-001 | Buyer Features | Favorites | Authenticated user can favorite approved listing | Logged-in Particular; approved listing. | Click favorite. | Favorite persists and UI reflects saved state. | Particular | E2E | Automated | P0 | Blocking | L179-L187 | BUILD | Not Run
FAV-002 | Buyer Features | Favorites | Authenticated user can unfavorite listing | Favorite exists. | Remove favorite. | Favorite row/state removed. | Particular | E2E | Automated | P1 | Blocking | L179-L187 | BUILD | Not Run
FAV-003 | Buyer Features | Favorites | Anonymous favorite action prompts/requires account | No session. | Attempt favorite. | No anonymous persistent favorite is created; user is guided to login. | Anonymous | E2E | Automated | P0 | Blocking | L179-L187 | BUILD | Not Run
FAV-004 | Buyer Features | Favorites | Duplicate favorite action is idempotent | Favorite already exists. | Repeat add/request. | Only one favorite relation exists. | Particular | DB/API | Automated | P1 | Blocking | L179-L187 | BUILD | Not Run
FAV-005 | Buyer Features | Favorites | Favorites account view lists saved items | User has favorites. | Open favorites. | Saved listings shown accurately. | Particular | E2E | Automated | P0 | Blocking | L179-L187 | BUILD | Not Run
FAV-006 | Buyer Features | Favorites | Favorite state appears on listing detail | Favorite exists. | Open detail. | Control reflects favorited state. | Particular | E2E | Automated | P1 | Blocking | L179-L187 | BUILD | Not Run
FAV-007 | Buyer Features | Favorites | Favorite state appears on supported listing cards | Favorite exists. | Browse catalog. | Supported cards reflect favorited state. | Particular | E2E | Automated | P1 | Blocking | L179-L187 | BUILD | Not Run
FAV-008 | Buyer Features | Favorites | Sold favorite remains in history with sold state | Favorited listing becomes sold. | Open favorites. | Item remains recognizable and marked unavailable/sold. | Particular | E2E | Automated | P1 | Blocking | L179-L187 | BUILD | Not Run
FAV-009 | Buyer Features | Favorites | Hidden favorite remains in history with availability state | Favorited listing becomes hidden. | Open favorites. | Item history is preserved where intended and current availability is clear. | Particular | E2E | Automated | P1 | Blocking | L179-L187 | BUILD | Not Run
FAV-010 | Buyer Features | Favorites | User cannot read another user's favorites | Two users. | Attempt data access. | RLS prevents cross-user favorite exposure. | Particular | DB/RLS | Automated | P0 | Blocking | L179-L187 | BUILD | Not Run
PDA-001 | Buyer Features | Price-drop alerts | Price decrease on favorited approved listing creates eligible alert | User favorites approved listing. | Seller lowers public price. | Notification event is created/sent once for new lower price. | Particular | Integration | Automated | P0 | Blocking | L185-L188 | BUILD | Not Run
PDA-002 | Buyer Features | Price-drop alerts | No alert when price unchanged | Favorited listing. | Save same price. | No price-drop notification. | Particular | Integration | Automated | P1 | Blocking | L185-L188 | BUILD | Not Run
PDA-003 | Buyer Features | Price-drop alerts | No alert when price increases | Favorited listing. | Raise price. | No price-drop notification. | Particular | Integration | Automated | P1 | Blocking | L185-L188 | BUILD | Not Run
PDA-004 | Buyer Features | Price-drop alerts | Same reduced price does not alert repeatedly | Price drop already notified. | Re-save unchanged reduced price. | No duplicate alert. | Particular | Integration | Automated | P0 | Blocking | L185-L188 | BUILD | Not Run
PDA-005 | Buyer Features | Price-drop alerts | Second later price drop can alert again | Earlier drop notified; price later reduced further. | Reduce again. | New lower-price event can notify once. | Particular | Integration | Automated | P1 | Blocking | L185-L188 | BUILD | Not Run
PDA-006 | Buyer Features | Price-drop alerts | Pending listing price change does not alert | Favorited/history relation; listing pending/nonpublic. | Change price. | No price-drop email. | Particular | Integration | Automated | P0 | Blocking | L185-L188 | BUILD | Not Run
PDA-007 | Buyer Features | Price-drop alerts | Rejected listing price change does not alert | Rejected listing. | Change internal price. | No alert. | Particular | Integration | Automated | P0 | Blocking | L185-L188 | BUILD | Not Run
PDA-008 | Buyer Features | Price-drop alerts | Hidden listing price change does not alert | Hidden favorited listing. | Change price. | No alert while hidden. | Particular | Integration | Automated | P0 | Blocking | L185-L188 | BUILD | Not Run
PDA-009 | Buyer Features | Price-drop alerts | Price-drop email links to correct listing | Eligible alert sent. | Open email link. | Correct listing destination opens with current availability. | Particular | E2E | Both | P1 | Blocking | L185-L188 | BUILD | Not Run
ALERT-001 | Buyer Features | Search alerts | Authenticated user can save exact search state | Logged-in user with filters/query. | Create alert. | Saved alert captures supported query/filter state accurately. | Particular | E2E | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-002 | Buyer Features | Search alerts | Anonymous user cannot create persistent search alert | No session. | Attempt create alert. | Login/account required. | Anonymous | E2E | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-003 | Buyer Features | Search alerts | Immediate alert fires for newly public matching listing | Immediate alert exists. | Approve/publish matching new listing. | User receives one immediate notification shortly after public availability. | Particular | Integration | Both | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-004 | Buyer Features | Search alerts | Immediate alert does not fire for nonmatching listing | Immediate alert exists. | Publish nonmatching listing. | No notification. | Particular | Integration | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-005 | Buyer Features | Search alerts | Daily digest bundles multiple new matches | Daily alert exists; several new matches. | Run daily job. | Single digest contains eligible new matches. | Particular | Integration | Both | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-006 | Buyer Features | Search alerts | Daily digest sends no empty email | Daily alert; no new matches. | Run scheduled job. | No email sent. | Particular | Integration | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-007 | Buyer Features | Search alerts | Same user-alert-listing is not notified twice | Alert has already notified listing. | Run alert evaluation again. | Dedup prevents repeat. | Particular | Integration | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-008 | Buyer Features | Search alerts | Pending listing does not trigger alert | Matching pending listing. | Run evaluation. | No alert until it becomes public. | Particular | Integration | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-009 | Buyer Features | Search alerts | Rejected listing does not trigger alert | Matching rejected listing. | Run evaluation. | No alert. | Particular | Integration | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-010 | Buyer Features | Search alerts | Hidden listing does not trigger new alert | Matching hidden listing. | Run evaluation. | No alert. | Particular | Integration | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-011 | Buyer Features | Search alerts | Listing triggers only when first newly public for alert semantics | Matching listing lifecycle. | Publish/re-save/revisit without genuinely new public event. | No repeated new-listing notification. | Particular | Integration | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
ALERT-012 | Buyer Features | Search alerts | User can pause alert | Active alert. | Pause then publish match. | No notifications while paused. | Particular | E2E | Automated | P1 | Blocking | L189-L193 | BUILD | Not Run
ALERT-013 | Buyer Features | Search alerts | User can resume paused alert without duplicate history | Paused alert with prior notifications. | Resume. | Future eligible matches notify; prior matches not replayed improperly. | Particular | Integration | Automated | P1 | Blocking | L189-L193 | BUILD | Not Run
ALERT-014 | Buyer Features | Search alerts | User can delete alert | Saved alert. | Delete then publish match. | Alert removed; no future notification. | Particular | E2E | Automated | P1 | Blocking | L189-L193 | BUILD | Not Run
ALERT-015 | Buyer Features | Search alerts | Alert email deep-links correctly | Alert email exists. | Open listing/search links. | Correct matching destination/filter state opens. | Particular | E2E | Both | P1 | Blocking | L189-L193 | BUILD | Not Run
ALERT-016 | Buyer Features | Search alerts | Alert cannot expose another user's saved search | Two users. | Attempt direct data query. | RLS/authorization isolates alerts. | Particular | DB/RLS | Automated | P0 | Blocking | L189-L193 | BUILD | Not Run
SEO-001 | Discovery | Category SEO pages | Real category page resolves without colliding with listing slug | Category route and listing slugs exist. | Open `/instrumentos/guitarras` and representative listing detail. | Both route to correct content. | Anonymous | E2E | Automated | P0 | Blocking | L195-L198 | BUILD | Not Run
SEO-002 | Discovery | Category SEO pages | Guitar category page uses real listing system | Approved guitar inventory exists. | Open category page. | Real filtered inventory appears, not static fake items. | Anonymous | E2E | Automated | P1 | Blocking | L195-L198 | BUILD | Not Run
SEO-003 | Discovery | Category SEO pages | Drum category page uses real listing system | Approved drum inventory exists. | Open category page. | Real filtered inventory appears. | Anonymous | E2E | Automated | P1 | Blocking | L195-L198 | BUILD | Not Run
SEO-004 | Discovery | Category SEO pages | Microphone category page uses real listing system | Approved microphone inventory exists. | Open category page. | Real filtered inventory appears. | Anonymous | E2E | Automated | P1 | Blocking | L195-L198 | BUILD | Not Run
SEO-005 | Discovery | Category SEO pages | Category filters/pagination remain functional | Many category listings. | Filter and paginate category page. | URL-driven marketplace behavior remains correct. | Anonymous | E2E | Automated | P1 | Blocking | L195-L198 | BUILD | Not Run
SEO-006 | Discovery | Category SEO pages | Category page is indexable when appropriate | Production-like environment. | Inspect metadata/robots. | Eligible category page is indexable and has category-specific metadata. | Anonymous | SEO | Both | P1 | Blocking | L195-L198 | BUILD | Not Run
SEO-007 | Discovery | Category SEO pages | No fake doorway content is generated | Category page. | Inspect content. | Page provides actual useful category browsing, not thin keyword-only content. | Anonymous | Manual | Manual | P1 | Blocking | L195-L198 | BUILD | Not Run
WA-001 | Analytics | WhatsApp contact tracking | Anonymous WhatsApp click still launches contact | Approved listing. | Click WhatsApp while logged out. | WhatsApp destination opens; anonymous contact remains allowed. | Anonymous | E2E | Both | P0 | Blocking | L199-L203 | BUILD | Not Run
WA-002 | Analytics | WhatsApp contact tracking | Authenticated WhatsApp click launches contact and records buyer intent | Logged-in user; approved listing. | Click WhatsApp. | Contact opens and event links buyer/listing/seller or store/timestamp. | Particular | Integration | Automated | P0 | Blocking | L199-L203 | BUILD | Not Run
WA-003 | Analytics | WhatsApp contact tracking | Store WhatsApp event attributes store correctly | Logged-in user; store listing. | Click contact. | Event references correct store/listing. | Particular | Integration | Automated | P0 | Blocking | L199-L203 | BUILD | Not Run
WA-004 | Analytics | WhatsApp contact tracking | Particular WhatsApp event attributes seller correctly | Logged-in user; individual listing. | Click contact. | Event references correct listing/seller identity. | Particular | Integration | Automated | P0 | Blocking | L199-L203 | BUILD | Not Run
WA-005 | Analytics | WhatsApp contact tracking | Contact event records timestamp | Logged-in or anonymous click. | Trigger event. | Timestamp stored accurately enough for eligibility/audit. | All | API/DB | Automated | P1 | Blocking | L199-L203 | BUILD | Not Run
WA-006 | Analytics | WhatsApp contact tracking | Useful source/context can be recorded without corrupting core identity | Open contact from supported surface. | Click. | Source/context is captured when provided; core attribution remains correct. | All | Integration | Automated | P2 | Non-blocking | L199-L203 | BUILD | Not Run
WA-007 | Analytics | WhatsApp contact tracking | WhatsApp message content is never recorded | Click contact. | Inspect request/event schema/logs. | No message body/content is persisted as analytics data. | All | Security | Automated | P0 | Blocking | L199-L203 | BUILD | Not Run
WA-008 | Analytics | WhatsApp contact tracking | Only authenticated contact event makes buyer eligible for verified transaction | Anonymous and authenticated contacts exist. | Mark listing sold and inspect eligible buyers. | Only authenticated contacted buyer is selectable. | Seller | Integration | Automated | P0 | Blocking | L199-L203 | BUILD | Not Run
WA-009 | Analytics | WhatsApp contact tracking | Unrelated authenticated user is not eligible | User never contacted listing. | Seller marks sold. | User does not appear as eligible buyer. | Seller | Integration | Automated | P0 | Blocking | L199-L203 | BUILD | Not Run
WA-010 | Analytics | WhatsApp contact tracking | Repeated contact clicks do not create duplicate eligible-buyer identities | Same buyer clicks several times. | Seller marks sold. | Buyer appears once as candidate while analytics may preserve event count. | Seller | Integration | Automated | P1 | Blocking | L199-L203 | BUILD | Not Run
AN-001 | Analytics | Marketplace funnel | Listing impression event is attributable to listing | Listing appears in supported browse surface. | Render qualifying impression. | Event/aggregate attributes correct listing. | Anonymous | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-002 | Analytics | Marketplace funnel | Listing detail view is counted correctly | Approved listing. | Open detail under defined dedup logic. | View/event count changes according to product rules, not runaway refreshes. | Anonymous | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-003 | Analytics | Marketplace funnel | Favorite add/remove events reconcile with favorite state | Logged-in user. | Add then remove favorite. | Analytics and canonical favorite data reconcile. | Particular | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-004 | Analytics | Marketplace funnel | Search event captures supported search state | Run marketplace search. | Submit search. | Event captures useful query/filter context without sensitive overcollection. | Anonymous | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-005 | Analytics | Marketplace funnel | Zero-result search is identified | Search yielding none. | Submit. | Zero-result event/metric recorded. | Anonymous | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-006 | Analytics | Marketplace funnel | Filter application is attributable | Apply filter. | Browse. | Filter event/state is captured consistently. | Anonymous | Integration | Automated | P2 | Non-blocking | L205-L215 | BUILD | Not Run
AN-007 | Analytics | Marketplace funnel | Store page view is attributable | Open active store page. | View. | Store analytics can count view. | Anonymous | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-008 | Analytics | Marketplace funnel | Listing creation funnel start/submission/approval/rejection states reconcile | Create/moderate test listings. | Progress lifecycle. | Events/states support funnel calculation without impossible ordering. | Particular | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-009 | Analytics | Marketplace funnel | Store application funnel states reconcile | Create/apply/approve/verify store. | Progress lifecycle. | Events support application funnel. | Store Owner | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-010 | Analytics | Marketplace funnel | Verified transaction event occurs only after buyer confirmation | Seller selects buyer. | Before and after buyer confirms. | No verified event before confirmation; one after. | All | Integration | Automated | P0 | Blocking | L205-L215 | BUILD | Not Run
AN-011 | Analytics | Marketplace funnel | Review submission event occurs once per side | Verified transaction. | Submit reviews. | Analytics do not duplicate canonical review state. | All | Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-012 | Analytics | Marketplace funnel | Listing CTR calculation is correct | Known impressions and opens. | Calculate/report metric. | CTR uses correct numerator/denominator. | Admin | Unit/Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-013 | Analytics | Marketplace funnel | Contact rate calculation is correct | Known opens and WhatsApp events. | Calculate. | Contact rate is correct. | Seller | Unit/Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-014 | Analytics | Marketplace funnel | Favorite rate calculation is correct | Known opens and favorite events. | Calculate. | Favorite rate is correct. | Seller | Unit/Integration | Automated | P1 | Blocking | L205-L215 | BUILD | Not Run
AN-015 | Analytics | Marketplace funnel | Zero-result rate calculation is correct | Known searches. | Calculate. | Metric is correct. | Admin | Unit/Integration | Automated | P2 | Non-blocking | L205-L215 | BUILD | Not Run
AN-016 | Analytics | Marketplace funnel | No invasive fingerprinting is required for anonymous analytics | Anonymous browsing. | Inspect analytics identifiers/implementation. | Uses privacy-conscious session/anonymous identifiers rather than invasive fingerprinting. | Anonymous | Security/Manual | Both | P0 | Blocking | L205-L215 | BUILD | Not Run
TX-001 | Transactions | Verified transaction confirmation | Marking sold prompts Laria-buyer question | Approved listing. | Seller marks sold. | Flow asks whether buyer came through Laria. | Seller | E2E | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-002 | Transactions | Verified transaction confirmation | Eligible buyer list contains only authenticated contacts for that listing | Several users/contact histories. | Mark sold. | Only qualifying contacted authenticated users appear. | Seller | Integration | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-003 | Transactions | Verified transaction confirmation | Seller cannot search full user directory from sale flow | Seller marks sold. | Inspect/interact with buyer selector. | No arbitrary directory search/browse is exposed. | Seller | Manual | Both | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-004 | Transactions | Verified transaction confirmation | Seller can choose outside-Laria/no-account option | Listing sold to external buyer. | Choose outside-Laria option. | Listing remains sold; no verified transaction or reviews created. | Seller | E2E | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-005 | Transactions | Verified transaction confirmation | Selecting eligible buyer creates pending confirmation request | Eligible buyer exists. | Seller selects buyer. | Pending confirmation relation created; buyer notification queued. | Seller | Integration | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-006 | Transactions | Verified transaction confirmation | Buyer sees correct listing/seller context in confirmation | Pending confirmation. | Buyer opens confirmation. | Correct sale context shown without claiming payment verification. | Buyer | E2E | Both | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-007 | Transactions | Verified transaction confirmation | Buyer confirmation yes creates verified transaction | Pending confirmation. | Buyer selects Sí, lo compré. | Exactly one verified transaction is created. | Buyer | Integration | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-008 | Transactions | Verified transaction confirmation | Buyer decline does not create verified transaction | Pending confirmation. | Buyer declines. | Listing remains sold; no verified transaction/review eligibility. | Buyer | E2E | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-009 | Transactions | Verified transaction confirmation | No response does not auto-verify transaction | Pending confirmation; no buyer action. | Allow time/no action. | Transaction remains unverified. | Buyer | Integration | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-010 | Transactions | Verified transaction confirmation | Buyer cannot confirm transaction assigned to another account | Two buyers. | Buyer B attempts A's confirmation link/API. | Denied. | Buyer | Security | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-011 | Transactions | Verified transaction confirmation | Seller cannot swap buyer after transaction verified | Verified transaction exists. | Attempt change buyer. | Historical verified relation remains immutable or follows explicit admin-only correction path. | Seller | DB/RLS | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-012 | Transactions | Verified transaction confirmation | Repeated yes confirmation is idempotent | Buyer already confirmed. | Repeat request. | No duplicate verified transaction. | Buyer | API/DB | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-013 | Transactions | Verified transaction confirmation | Verified transaction does not verify price/payment/delivery | Verified transaction exists. | Inspect UI/copy. | Copy accurately limits what verification means. | All | Manual | Manual | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-014 | Transactions | Verified transaction confirmation | Verified transaction remains attached to original sold listing after relist | Verified sold listing relisted. | Inspect relations. | Transaction remains linked to original history, not new copy. | Admin | DB | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-015 | Transactions | Verified transaction confirmation | Store transaction seller identity is the store | Store listing sold/confirmed. | Inspect verified relation. | Seller-side entity for review is store. | Buyer | DB | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
TX-016 | Transactions | Verified transaction confirmation | Particular transaction seller identity is Particular account | Individual listing sold/confirmed. | Inspect relation. | Seller-side entity is Particular account. | Buyer | DB | Automated | P0 | Blocking | L217-L230 | BUILD | Not Run
REVW-001 | Reviews | Two-way double-blind | Verified transaction unlocks buyer review of seller/store | Verified transaction. | Open review flow as buyer. | Review form available. | Buyer | E2E | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-002 | Reviews | Two-way double-blind | Verified transaction unlocks seller/store review of buyer | Verified transaction. | Open review flow as seller. | Review form available. | Seller | E2E | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-003 | Reviews | Two-way double-blind | Unverified sold listing does not unlock reviews | Sold but unverified transaction. | Open review flow. | Reviews unavailable. | All | E2E | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-004 | Reviews | Two-way double-blind | Rating requires integer/valid 1–5 value | Verified transaction. | Submit missing/out-of-range rating. | Rejected. | All | API | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-005 | Reviews | Two-way double-blind | Optional comment may be blank | Verified transaction. | Submit valid stars with no comment. | Review accepted. | All | E2E | Automated | P1 | Blocking | L232-L240 | BUILD | Not Run
REVW-006 | Reviews | Two-way double-blind | One buyer review per transaction | Buyer already reviewed. | Submit again. | Duplicate rejected/idempotent according to API design. | Buyer | DB | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-007 | Reviews | Two-way double-blind | One seller review per transaction | Seller already reviewed. | Submit again. | Duplicate rejected/idempotent. | Seller | DB | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-008 | Reviews | Two-way double-blind | First review remains hidden while other side can still submit | Only one side reviewed before deadline. | View as counterparty/public. | Review content/rating is not revealed. | All | E2E | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-009 | Reviews | Two-way double-blind | Both reviews reveal immediately when both submit | Both sides submit before 10 days. | Refresh review surfaces. | Both become visible together. | All | Integration | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-010 | Reviews | Two-way double-blind | Single submitted review reveals after 10-day window | One side submitted; other did not. | Advance scheduler/time past 10 days. | Submitted review becomes public/visible per rules. | All | Integration | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-011 | Reviews | Two-way double-blind | No review can be submitted after defined window if workflow closes at 10 days | Verified transaction >10 days. | Attempt new review. | Behavior follows fixed review-window rule consistently. | All | Integration | Automated | P1 | Blocking | L232-L240 | BUILD | Not Run
REVW-012 | Reviews | Two-way double-blind | Counterparty cannot infer hidden rating before reveal | One hidden review exists. | Inspect APIs/UI as other side. | No stars/comment/aggregate leakage reveals hidden review. | All | Security | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-013 | Reviews | Two-way double-blind | Published review cannot be freely edited | Published review. | Attempt edit. | User edit is denied. | All | DB/RLS | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-014 | Reviews | Two-way double-blind | Published review cannot be freely deleted | Published review. | Attempt delete. | User delete is denied. | All | DB/RLS | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-015 | Reviews | Two-way double-blind | User can report published review | Visible review. | Report it. | Report enters moderation system. | All | E2E | Automated | P1 | Blocking | L232-L240 | BUILD | Not Run
REVW-016 | Reviews | Two-way double-blind | Admin can hide abusive review without rewriting it | Published review. | Admin hides. | Review becomes nonpublic; original text remains immutable/auditable. | Admin | E2E | Automated | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-017 | Reviews | Two-way double-blind | Admin cannot edit review body through normal moderation UI | Published review. | Inspect admin actions. | Only hide/resolve actions exist; no rewrite action. | Admin | Manual | Both | P0 | Blocking | L232-L240 | BUILD | Not Run
REVW-018 | Reviews | Two-way double-blind | Store rating aggregates against store entity | Multiple verified store reviews. | Inspect store rating. | Aggregation belongs to store. | Anonymous | Integration | Automated | P1 | Blocking | L232-L240 | BUILD | Not Run
REVW-019 | Reviews | Two-way double-blind | Particular rating aggregates against Particular seller identity | Multiple verified individual reviews. | Inspect seller rating. | Aggregation belongs to Particular account. | Anonymous | Integration | Automated | P1 | Blocking | L232-L240 | BUILD | Not Run
REVW-020 | Reviews | Two-way double-blind | Review UI does not claim Laria processed transaction | Published reviews. | Inspect labels/help. | Wording preserves off-platform transaction limitation. | Anonymous | Manual | Manual | P0 | Blocking | L232-L240 | BUILD | Not Run
REP-001 | Trust & Safety | Reports | User can report listing | Reportable listing. | Submit fixed reason + optional detail. | Report created with target listing, reason, timestamp and reporter where applicable. | User | E2E | Automated | P0 | Blocking | L242-L244 | BUILD | Not Run
REP-002 | Trust & Safety | Reports | User can report store | Public store. | Submit report. | Report created with correct target. | User | E2E | Automated | P1 | Blocking | L242-L244 | BUILD | Not Run
REP-003 | Trust & Safety | Reports | User can report review | Published review. | Submit report. | Report created with correct review target. | User | E2E | Automated | P0 | Blocking | L242-L244 | BUILD | Not Run
REP-004 | Trust & Safety | Reports | Fixed reason is required | Report flow. | Submit without reason. | Rejected. | User | E2E | Automated | P1 | Blocking | L242-L244 | BUILD | Not Run
REP-005 | Trust & Safety | Reports | Optional detail may be blank | Report flow. | Submit fixed reason only. | Accepted. | User | E2E | Automated | P1 | Blocking | L242-L244 | BUILD | Not Run
REP-006 | Trust & Safety | Reports | Report timestamp is recorded | Submit report. | Inspect record. | Timestamp present. | Admin | DB | Automated | P2 | Non-blocking | L242-L244 | BUILD | Not Run
REP-007 | Trust & Safety | Reports | Reporter identity is associated where applicable | Logged-in reporter. | Submit. | Reporter id is stored according to policy. | User | DB | Automated | P1 | Blocking | L242-L244 | BUILD | Not Run
REP-008 | Trust & Safety | Reports | Admin can resolve report | Open report in admin. | Resolve. | Status changes and report leaves active queue appropriately. | Admin | E2E | Automated | P0 | Blocking | L242-L244 | BUILD | Not Run
REP-009 | Trust & Safety | Reports | Admin can dismiss report | Open report. | Dismiss. | Status records dismissal without mutating target automatically unless separately acted upon. | Admin | E2E | Automated | P1 | Blocking | L242-L244 | BUILD | Not Run
REP-010 | Trust & Safety | Reports | Ordinary user cannot read moderation queue | Logged-in nonadmin. | Attempt reports admin data access. | Denied. | User | DB/RLS | Automated | P0 | Blocking | L242-L244 | BUILD | Not Run
ADMIN-001 | Admin | Operational moderation hub | Nonadmin cannot access admin hub | Logged-in nonadmin. | Open `/admin`. | Access denied/redirected. | Particular | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Pass | Owner production/manual regression PASS; Sprint 2 checks preserved — 2026-09-10
ADMIN-002 | Admin | Operational moderation hub | Admin can search/filter all listings | Admin; varied listing states. | Use admin listing search/filter. | Results include correct records/states. | Admin | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Not Run
ADMIN-003 | Admin | Operational moderation hub | Admin can search/filter all stores | Admin; varied stores. | Use store search/filter. | Correct stores/states shown. | Admin | E2E | Automated | P1 | Blocking | L246-L252 | MODIFY | Not Run
ADMIN-004 | Admin | Operational moderation hub | Admin can inspect user accounts | Admin. | Open users area. | Required account metadata visible without exposing secrets. | Admin | E2E | Automated | P1 | Blocking | L246-L252 | MODIFY | Not Run
ADMIN-005 | Admin | Operational moderation hub | Admin can inspect pending revisions | Pending revision exists. | Open revision queue. | Correct live vs proposed values visible. | Admin | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
ADMIN-006 | Admin | Operational moderation hub | Admin can inspect reports | Open reports area. | Filter/open report. | Target and reason context available. | Admin | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Not Run
ADMIN-007 | Admin | Operational moderation hub | Admin can inspect reviews | Reviews exist. | Open reviews area. | Review state/target/visibility available. | Admin | E2E | Automated | P1 | Blocking | L246-L252 | MODIFY | Not Run
ADMIN-008 | Admin | Operational moderation hub | Admin can inspect verified transactions | Verified/unverified sale relationships exist. | Open transactions area. | Correct transaction confirmation state visible. | Admin | E2E | Automated | P1 | Blocking | L246-L252 | MODIFY | Not Run
ADMIN-009 | Admin | Operational moderation hub | Admin can manage store verification | Active store. | Verify/revoke. | Privileges change according to spec. | Admin | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Pass | Automated local SQL/RLS compatibility PASS — 2026-09-10
ADMIN-010 | Admin | Operational moderation hub | Listing rejection requires reason | Pending listing. | Attempt reject without reason. | Action blocked. | Admin | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
ADMIN-011 | Admin | Operational moderation hub | Listing rejection reason is visible to owner | Rejected listing with reason. | Owner opens account. | Reason shown. | Particular | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
ADMIN-012 | Admin | Operational moderation hub | Administrative hide requires reason | Approved listing. | Attempt hide without reason. | Action blocked. | Admin | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Pass | Owner manual production acceptance PASS — 2026-09-15
ADMIN-013 | Admin | Operational moderation hub | Store rejection requires reason and owner sees it | Pending store. | Reject with reason, open owner dashboard. | Reason persists and is visible. | Admin | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Pass | Automated local SQL/RLS compatibility PASS — 2026-09-10
ADMIN-014 | Admin | Operational moderation hub | Admin can manually link legacy listing ownership | Legacy unowned listing + selected account. | Assign ownership. | owner_user_id links only to chosen account; audit/history preserved. | Admin | E2E | Automated | P0 | Blocking | L246-L252 | MODIFY | Not Run
ADMIN-015 | Admin | Operational moderation hub | Legacy ownership is never auto-linked from phone/email alone | Matching legacy contact exists. | Create account/run background jobs. | No automatic ownership assignment occurs. | Admin | DB | Automated | P0 | Blocking | L246-L252 | MODIFY | Pass | Automated local SQL/RLS compatibility PASS — 2026-09-10
ADMIN-016 | Admin | Operational moderation hub | Admin cannot expose auth secrets in UI/logs | Admin hub/users. | Inspect network/UI/log output. | Passwords/tokens/service-role secrets never displayed. | Admin | Security | Both | P0 | Blocking | L246-L252 | MODIFY | Pass | Owner production/manual regression PASS; Sprint 2 checks preserved — 2026-09-10
MAIL-001 | Notifications | Application email | Listing approval sends/queues marketplace email | Owner listing approved. | Approve. | Owner receives/queues approval notification once. | Particular | Integration | Both | P0 | Blocking | L254-L258 | BUILD | Not Run
MAIL-002 | Notifications | Application email | Listing rejection sends/queues email with useful status context | Owner listing rejected. | Reject with reason. | Owner receives/queues rejection notification. | Particular | Integration | Both | P0 | Blocking | L254-L258 | BUILD | Not Run
MAIL-003 | Notifications | Application email | Store approval sends/queues status email | Pending store approved. | Approve. | Store owner notified. | Store Owner | Integration | Both | P1 | Blocking | L254-L258 | BUILD | Not Run
MAIL-004 | Notifications | Application email | Store rejection sends/queues status email | Pending store rejected. | Reject. | Store owner notified. | Store Owner | Integration | Both | P1 | Blocking | L254-L258 | BUILD | Not Run
MAIL-005 | Notifications | Application email | Verification change notification is sent where useful | Store verification granted/revoked. | Change status. | Owner receives appropriate lifecycle notice without duplicate spam. | Store Owner | Integration | Both | P1 | Blocking | L254-L258 | BUILD | Not Run
MAIL-006 | Notifications | Application email | Buyer transaction-confirmation email targets selected buyer only | Seller selects buyer. | Trigger confirmation. | Only selected eligible buyer gets request. | Buyer | Integration | Both | P0 | Blocking | L254-L258 | BUILD | Not Run
MAIL-007 | Notifications | Application email | Review workflow notification respects double-blind rules | Verified transaction/review milestones. | Trigger notifications. | Emails do not reveal hidden counterparty rating/comment. | All | Integration | Both | P0 | Blocking | L254-L258 | BUILD | Not Run
MAIL-008 | Notifications | Application email | Search immediate email is deduplicated | Immediate alert event. | Retry job/provider callback. | At most one logical notification per user-alert-listing. | Particular | Integration | Automated | P0 | Blocking | L254-L258 | BUILD | Not Run
MAIL-009 | Notifications | Application email | Daily digest deduplicates items | Daily matches include repeats. | Run digest. | Each qualifying listing appears once. | Particular | Integration | Automated | P0 | Blocking | L254-L258 | BUILD | Not Run
MAIL-010 | Notifications | Application email | Price-drop email deduplicates unchanged price | Already alerted price. | Re-run job. | No repeat alert. | Particular | Integration | Automated | P0 | Blocking | L254-L258 | BUILD | Not Run
MAIL-011 | Notifications | Application email | Application product logic is provider-abstracted | Email implementation exists. | Inspect integration boundary/tests. | Marketplace workflow does not hard-code provider semantics throughout domain logic. | Developer | Code Review | Manual | P1 | Blocking | L254-L258 | BUILD | Not Run
MAIL-012 | Notifications | Application email | Email delivery failure does not corrupt core marketplace state | Force provider failure. | Approve listing/confirm transaction/etc. | Core state transition remains consistent; retry/error is observable. | Admin | Integration | Automated | P0 | Blocking | L254-L258 | BUILD | Not Run
LEGAL-001 | Legal & Safety | Required pages/copy | Terms/marketplace rules page exists | App deployed. | Open Terms route. | Dedicated content is accessible. | Anonymous | E2E | Automated | P0 | Blocking | L260-L264 | BUILD | Not Run
LEGAL-002 | Legal & Safety | Required pages/copy | Privacy Policy page exists | App deployed. | Open Privacy route. | Dedicated content is accessible. | Anonymous | E2E | Automated | P0 | Blocking | L260-L264 | BUILD | Not Run
LEGAL-003 | Legal & Safety | Required pages/copy | Prohibited-item rules page exists | App deployed. | Open prohibited-items route. | Dedicated content is accessible. | Anonymous | E2E | Automated | P1 | Blocking | L260-L264 | BUILD | Not Run
LEGAL-004 | Legal & Safety | Required pages/copy | Marketplace safety page exists | App deployed. | Open safety route. | Dedicated safety guidance is accessible. | Anonymous | E2E | Automated | P1 | Blocking | L260-L264 | BUILD | Not Run
LEGAL-005 | Legal & Safety | Required pages/copy | Safety copy states Laria does not process payments/escrow/shipping | Relevant safety/trust surfaces. | Inspect copy. | Limitation is explicit. | Anonymous | Manual | Manual | P0 | Blocking | L260-L264 | BUILD | Not Run
LEGAL-006 | Legal & Safety | Required pages/copy | Trust copy does not guarantee transaction outcome | Relevant pages. | Inspect copy. | No wording implies Laria guarantees payment, delivery, condition or transaction. | Anonymous | Manual | Manual | P0 | Blocking | L260-L264 | BUILD | Not Run
REL-001 | Reliability | Preserve September 2026 baseline | Catalog uses 24-item pages | More than 24 approved listings. | Browse pages. | Exactly bounded page behavior with navigation. | Anonymous | E2E | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-002 | Reliability | Preserve September 2026 baseline | Store inventory uses 24-item pages | Store has >24 approved listings. | Open store pages. | Bounded stable pagination works. | Anonymous | E2E | Automated | P1 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-003 | Reliability | Preserve September 2026 baseline | Pagination preserves filters | Filtered catalog >1 page. | Navigate page 2/back. | Filter/query state preserved. | Anonymous | E2E | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-004 | Reliability | Preserve September 2026 baseline | Pagination ordering is deterministic | Listings with tied primary sort fields. | Reload/navigate repeatedly. | Stable ID tie-breaker prevents duplicates/omissions. | Anonymous | Integration | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-005 | Reliability | Preserve September 2026 baseline | Photo count supports >1000 photos without truncation | Large seeded photo set. | Query count behavior. | Database-computed counts remain correct beyond row cap. | Developer | DB | Automated | P1 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-006 | Reliability | Preserve September 2026 baseline | Recommendations do not block primary listing content | Listing with recommendation queries. | Simulate slow secondary queries. | Primary product renders first; recommendations stream later. | Anonymous | Performance | Automated | P1 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-007 | Reliability | Preserve September 2026 baseline | Public browsing avoids unnecessary authenticated getUser network work | Signed-in user browses public page. | Inspect server behavior. | Public route does not perform needless auth validation beyond intended middleware policy. | Particular | Performance | Automated | P1 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-008 | Reliability | Preserve September 2026 baseline | Approval sets first publication timestamp | Pending listing. | Approve. | published_at is populated once. | Admin | DB | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-009 | Reliability | Preserve September 2026 baseline | Reapproval preserves original publication timestamp | Previously approved listing cycles state as allowed. | Reapprove. | Original first publication timestamp remains. | Admin | DB | Automated | P1 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-010 | Reliability | Preserve September 2026 baseline | Signup duplicate-email lookup is targeted and failure-safe | Existing/unknown emails; force DB lookup failure. | Call precheck. | No directory scan; failure never returns false 'available'. | Anonymous | API | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-011 | Reliability | Preserve September 2026 baseline | Submission finalization is atomic | Force failure during finalization. | Submit. | No partial listing/photo relational state is committed. | Particular | DB/Integration | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-012 | Reliability | Preserve September 2026 baseline | Submission finalization is idempotent | Same submission ID finalized twice. | Retry. | One logical record only. | Particular | DB/Integration | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-013 | Reliability | Preserve September 2026 baseline | Partial upload cleanup attempts run | Force upload failure after some files. | Observe recovery. | Cleanup attempted and retry remains possible. | Particular | Integration | Automated | P1 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-014 | Reliability | Preserve September 2026 baseline | Existing regression suite passes after each sprint | Repository with sprint changes. | Run npm tests + DB regression suite. | All baseline regression tests pass. | Developer | CI | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
REL-015 | Reliability | Preserve September 2026 baseline | Build/lint/typecheck pass | Repository state. | Run npm run lint, typecheck, build. | All commands pass. | Developer | CI | Automated | P0 | Blocking | L286-L302 | DONE | Pass | Automated local regression PASS — 2026-09-10
SCOPE-001 | V1 Scope | Out-of-scope guardrails | No Laria checkout is exposed | App surfaces. | Inspect purchase flow. | No in-platform checkout/payment collection exists. | All | Manual | Manual | P0 | Blocking | L266-L278 | DONE | Not Run
SCOPE-002 | V1 Scope | Out-of-scope guardrails | No escrow workflow is exposed | App surfaces. | Inspect transaction flow. | No escrow claim/feature exists. | All | Manual | Manual | P0 | Blocking | L266-L278 | DONE | Not Run
SCOPE-003 | V1 Scope | Out-of-scope guardrails | No shipping-management workflow is exposed | App surfaces. | Inspect listing/account flow. | No Laria shipping orchestration exists. | All | Manual | Manual | P1 | Blocking | L266-L278 | DONE | Not Run
SCOPE-004 | V1 Scope | Out-of-scope guardrails | No transaction commission enforcement exists | Seller/store flows. | Inspect lifecycle/fees. | No V1 commission collection/enforcement. | All | Manual | Manual | P1 | Blocking | L266-L278 | DONE | Not Run
SCOPE-005 | V1 Scope | Out-of-scope guardrails | No paid subscription/boost purchase exists | Store/listing account surfaces. | Inspect plans/actions. | V1 remains free; no purchasable plan/boost workflow. | All | Manual | Manual | P0 | Blocking | L266-L278 | DONE | Not Run
SCOPE-006 | V1 Scope | Out-of-scope guardrails | No internal messaging/chat exists as working feature | App surfaces. | Inspect contact flows. | WhatsApp remains external communication path. | All | Manual | Manual | P1 | Blocking | L266-L278 | DONE | Not Run
SCOPE-007 | V1 Scope | Out-of-scope guardrails | No multi-employee store management UI is active | Store dashboard. | Inspect member management. | One effective owner account is the V1 supported workflow. | Store Owner | Manual | Manual | P2 | Non-blocking | L266-L278 | DONE | Not Run
SCOPE-008 | V1 Scope | Out-of-scope guardrails | No automatic SUNAT verification is claimed | Store verification. | Inspect workflow/copy. | Verification remains manual admin process. | Admin | Manual | Manual | P1 | Blocking | L266-L278 | DONE | Not Run
REV-017 | Listings | Approved listing editing | Pending moderated revision is amended in place | Approved listing has a pending title proposal. | Change the proposed title again and add a moderated condition change. | The same pending revision ID is retained, its version increases, and it contains the latest proposal. | Particular | DB/Integration | Automated | P0 | Blocking | L117-L137 | DONE | Pass | Automated local Sprint 3.1 regression PASS — 2026-09-16
REV-018 | Listings | Approved listing editing | Pending revision photo set can be amended | Approved listing has a pending moderated proposal and valid live photos. | Add, remove, reorder or replace proposed photos and save. | The same pending proposal contains the latest isolated photo set; live photos remain unchanged until approval. | Particular | DB/Integration | Automated | P0 | Blocking | L117-L137 | DONE | Pass | Automated local Sprint 3.1 regression PASS — 2026-09-16
REV-019 | Listings | Approved listing editing | Stale admin revision decision is denied | Admin loaded revision version N; owner amends it to N+1. | Admin attempts approval or rejection using version N. | The decision fails safely and admin must reload the latest proposal. | Admin | DB/Integration | Automated | P0 | Blocking | L117-L137 | DONE | Pass | Automated local Sprint 3.1 regression PASS — 2026-09-16
LIST-023 | Listings | Particular listing creation | Whole-sol price round-trips exactly | Seller enters a valid price such as S/ 1,200. | Submit, query stored/API value, then open catalog card and detail page; repeat after price edit. | Entered, stored, API and rendered values remain exactly S/ 1,200, with no fee or numeric-control mutation. | Particular | Integration | Automated | P0 | Blocking | L59-L79 | DONE | Pass | Automated local Sprint 3.1 regression PASS — 2026-09-16
STORE-018 | Stores | Application and ownership | Duplicate RUC shows an explicit private reason | Another store already owns the normalized RUC. | Submit the duplicate RUC through the store application. | Submission is blocked and UI states that the RUC is already registered without exposing owner data. | Store Owner | Integration | Automated | P1 | Blocking | L139-L154 | DONE | Pass | Automated local Sprint 3.1 regression PASS — 2026-09-16
DASH-008 | Particular Dashboard | Account result notices | Page-level action notice receives focus and is scrolled into view | Account/admin form returns a top-level success or actionable error. | Complete the form while its notice location is outside the viewport. | The shared notice receives accessible focus and scrolls into view; field-level errors do not cause global scrolling. | All | Component | Automated | P1 | Blocking | L99-L115 | DONE | Pass | Automated local Sprint 3.1 regression PASS — 2026-09-16
NOTIF-001 | Notifications | In-app account notifications | Notification visibility, RLS and read state are owner-scoped | Two authenticated owners and supported lifecycle events exist. | Read notifications as each owner and anonymous; mark one notification read. | Each owner sees only their newest-first notifications; anonymous sees none; read state changes without mutable event/ownership metadata. | Particular / Store Owner | DB/Integration | Automated | P0 | Blocking | L254-L258 | DONE | Pass | Automated local Sprint 3.1 regression PASS — 2026-09-16
NOTIF-002 | Notifications | In-app account notifications | Revision rejection notification leads to its reason | Admin rejects an amended listing revision with a reason. | Open the owner notification and follow its target. | A typed rejection notice links to the owner's listing area where the rejection reason is reachable. | Particular / Store Owner | Integration | Automated | P1 | Blocking | L254-L258 | DONE | Pass | Automated local Sprint 3.1 regression PASS — 2026-09-16

## Coverage Summary
Laria V1 Acceptance Coverage
KPI | Value | Domain | Cases | P0
Total test cases | 357 | Public Marketplace | 7 | 5
P0 cases | 229 | Accounts & Authentication | 22 | 15
Blocking cases | 349 | Listings | 73 | 51
Automated | 307 | Security & Ownership | 12 | 12
Manual | 23 | Particular Dashboard | 8 | 3
Both | 27 | Analytics | 36 | 12
Passed | 116 | Stores | 42 | 30
Failed | 4 | Store Dashboard | 10 | 7
Blocked | 1 | Buyer Features | 35 | 21
Deferred | 0 | Discovery | 7 | 1
N/A | 0 | Transactions | 16 | 16
Not Run | 236 | Reviews | 20 | 15
|  | Trust & Safety | 10 | 4
|  | Admin | 16 | 12
|  | Notifications | 14 | 9
|  | Legal & Safety | 6 | 4
|  | Reliability | 15 | 9
|  | V1 Scope | 8 | 3

## Test Personas
Fixture | Role | Purpose | Minimum Setup
ANON | Anonymous visitor | Public browsing, public WhatsApp, auth gates | No session
P-A | Particular A | Primary buyer/seller happy paths | Confirmed Particular profile with WhatsApp/city/region
P-B | Particular B | Cross-user authorization and review/contact scenarios | Separate confirmed Particular profile
P-C | Particular C | Eligible buyer for verified-transaction tests | Confirmed account + WhatsApp contact event on target listing
STORE-N | Normal Tienda owner | Moderated store inventory | Store-owner account + approved nonverified store
STORE-V | Tienda Verificada owner | Direct publication and edit bypass | Store-owner account + active verified store
STORE-P | Pending store owner | Pre-approval submission behavior | Store-owner account + pending store
ADMIN | Admin | Moderation, verification, linking, reports | Auth user with app_metadata.role='admin'
LEGACY | Legacy unowned listing | Historical contact fallback/manual ownership | Listing owner_user_id=NULL with listing-level contact fields
LIST-A | Approved Particular listing | Lifecycle/edit/favorite/contact tests | Owned approved listing with >=2 photos
LIST-S | Sold listing | Direct URL/relist/transaction history | Sold listing with stable slug
TX-V | Verified transaction | Review workflow | Sold listing + eligible buyer + buyer confirmation

## Spec Traceability
Spec Section | Spec Lines | Mapped Test Prefixes | Notes
Product Model | L12-L25 | PUB, SCOPE | Public discovery model and V1 exclusions
Account Types / Authentication | L27-L57 | AUTH | Particular, Store Owner, Admin and auth completeness
Particular Listing Creation | L59-L79 | LIST, PHOTO | Account-required listing creation and 2–10 photos
Listing Lifecycle | L81-L97 | LIFE | Hidden, sold, immutable history, relist copy
Particular Dashboard / Profile | L99-L115 | DASH, SANA, LIST | Management, analytics, dynamic profile fallback
Approved Listing Editing | L117-L137 | REV | Immediate vs moderated edits; live version preserved
Store Account / Application | L139-L154 | STORE | Owner binding, required business data, unique RUC
Store Approval / Verification | L156-L165 | VERIFY | Tienda vs Tienda Verificada
Store Cap | L167-L171 | CAP | 50 concurrent pending+approved
Store Dashboard | L173-L177 | SDASH | Inventory/profile/commercial analytics
Favorites / Alerts | L179-L193 | FAV, PDA, ALERT | Favorites, price drops, search alerts
Category SEO | L195-L198 | SEO | Real category browsing, route collision prevention
WhatsApp Tracking | L199-L203 | WA | Intent events and buyer eligibility
Marketplace Analytics | L205-L215 | AN, SANA, SDASH | Primary funnel and derived metrics
Verified Transactions | L217-L230 | TX | Contact-qualified buyer confirmation
Reviews | L232-L240 | REVW | Two-way, double-blind, 10-day window
Reports | L242-L244 | REP | Listing/store/review reports
Admin Hub | L246-L252 | ADMIN | Operational moderation hub
Email Notifications | L254-L258 | MAIL, NOTIF | Marketplace email infrastructure plus in-app account lifecycle notifications
Legal / Safety | L260-L264 | LEGAL | Required pages and disclaimers
Out of V1 | L266-L278 | SCOPE | Guardrails against feature creep
Reliability Baseline | L286-L302 | REL | September 2026 performance/reliability invariants